## Sheet1
 | time axis 2023-01-31 to 2023-06-05
Title | Start Date | End Date | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-04 | 2023-02-05 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | 2023-02-18 | 2023-02-19 | 2023-02-20 | 2023-02-21 | 2023-02-22 | 2023-02-23 | 2023-02-24 | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-03 | 2023-03-04 | 2023-03-05 | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-09 | 2023-03-10 | 2023-03-11 | 2023-03-12 | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 2023-03-18 | 2023-03-19 | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-25 | 2023-03-26 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 2023-04-01 | 2023-04-02 | 2023-04-03 | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-07 | 2023-04-08 | 2023-04-09 | 2023-04-10 | 2023-04-11 | 2023-04-12 | 2023-04-13 | 2023-04-14 | 2023-04-15 | 2023-04-16 | 2023-04-17 | 2023-04-18 | 2023-04-19 | 2023-04-20 | 2023-04-21 | 2023-04-22 | 2023-04-23 | 2023-04-24 | 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-04-29 | 2023-04-30 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 | 2023-05-06 | 2023-05-07 | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-13 | 2023-05-14 | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-19 | 2023-05-20 | 2023-05-21 | 2023-05-22 | 2023-05-23 | 2023-05-24 | 2023-05-25 | 2023-05-26 | 2023-05-27 | 2023-05-28 | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-06-01 | 2023-06-02 | 2023-06-03 | 2023-06-04 | 2023-06-05
Preparation | 2023-01-31 | 2023-02-06 | bar: 2023-01-31 to 2023-02-06
Interview Draft | 2023-01-31 | 2023-01-31 | bar: 2023-01-31
Contact people for interviews | 2023-01-31 | 2023-01-31 | bar: 2023-01-31
Research initial UX methods | 2023-01-31 | 2023-02-02 | bar: 2023-01-31 to 2023-02-02
Research Image Analysis methods | 2023-01-31 | 2023-02-02 | bar: 2023-01-31 to 2023-02-02
Create Git repository | 2023-01-31 | 2023-01-31 | bar: 2023-01-31
Create Overleaf document for final report | 2023-01-31 | 2023-01-31 | bar: 2023-01-31
Look into using wheel from bike to rotate | 2023-02-02 | 2023-02-06 | bar: 2023-02-02 to 2023-02-06
Finish expert interview | 2023-02-02 | 2023-02-06 | bar: 2023-02-02 to 2023-02-06
Start writing inital part of report | 2023-02-02 | 2023-02-06 | bar: 2023-02-02 to 2023-02-06
Fill in Gantt diagram | 2023-02-02 | 2023-02-06 | bar: 2023-02-02 to 2023-02-06
Talk about Gantt diagram and mid-project goals | 2023-02-07 | 2023-02-07 | bar: 2023-02-07
Android app prototype | 2023-02-02 | 2023-02-07 | bar: 2023-02-02 to 2023-02-06
Send email to Daniel | 2023-02-02 | 2023-02-02 | bar: 2023-02-02
Iteration 1 - Ground Truth | 2023-02-07 | 2023-02-13 | bar: 2023-02-07 to 2023-02-13
Plan wheel data collection | 2023-02-07 | 2023-02-07 | bar: 2023-02-07
Create rotating wheel setup | 2023-02-08 | 2023-02-08 | bar: 2023-02-08
Execute wheel data collection | 2023-02-09 | 2023-02-09 | bar: 2023-02-09
Offline analysis of bike wheel data | 2023-02-10 | 2023-02-12 | bar: 2023-02-10 to 2023-02-12
Write BML#1 section in report | 2023-02-11 | 2023-02-13 | bar: 2023-02-11 to 2023-02-13
Dennis interview | 2023-02-13 | 2023-02-13 | bar: 2023-02-13
Learn meeting | 2023-02-13 | 2023-02-13
Iteration 2 - Offline Linear Analysis | 2023-02-14 | 2023-02-20 | bar: 2023-02-14 to 2023-02-20
Per Meeting #2 | 2023-02-16 | 2023-02-16 | bar: 2023-02-16
Plan and execute linear experiment | 2023-02-14 | 2023-02-14 | bar: 2023-02-14
Conduct offline analysis | 2023-02-15 | 2023-02-17 | bar: 2023-02-15 to 2023-02-17
Write BML#2 section in report | 2023-02-15 | 2023-02-20 | bar: 2023-02-15 to 2023-02-20
Write Kotlin vs. Java section | 2023-02-18 | 2023-02-18 | bar: 2023-02-18
Learn meeting | 2023-02-19 | 2023-02-19 | bar: 2023-02-19
Iteration 3 - Simple Linear App | 2023-02-21 | 2023-02-27 | bar: 2023-02-21 to 2023-02-27
Collect accelerometer data | 2023-02-21 | 2023-02-22 | bar: 2023-02-20 to 2023-02-22
Collect gyroscopic data | 2023-02-23 | 2023-02-24 | bar: 2023-02-23 to 2023-02-24
Collect optical data | 2023-02-21 | 2023-02-24 | bar: 2023-02-21 to 2023-02-24
Research different eye detection packages and pick one | 2023-02-25 | 2023-02-27 | bar: 2023-02-25 to 2023-02-27
Write BML#3 Section In Report | 2023-02-21 | 2023-03-06 | bar: 2023-02-20 to 2023-02-28
Iteration 3 - Simple Linear App | 2023-02-28 | 2023-03-06 | bar: 2023-02-28 to 2023-03-06
Write BML#3 Section In Report | 2023-02-21 | 2023-03-06 | bar: 2023-02-28 to 2023-03-06
Implement eye detection package | 2023-02-28 | 2023-03-02 | bar: 2023-02-28 to 2023-03-02
Conduct experiment | 2023-03-03 | 2023-03-03 | bar: 2023-03-03
Learn Meeting | 2023-03-05 | 2023-03-05 | bar: 2023-03-05
Hand in project plan | 2023-03-01 | 2023-03-01 | bar: 2023-03-01
Iteration 4 - End User Testing 1 | 2023-03-07 | 2023-03-13 | bar: 2023-03-07 to 2023-03-13
Create Lean Canvas | 2023-03-07 | 2023-03-07 | bar: 2023-03-07
Create Roleplaying Test | 2023-03-08 | 2023-03-08 | bar: 2023-03-08
Test on friends, colleagues, family members and strangers | 2023-03-09 | 2023-03-13 | bar: 2023-03-09 to 2023-03-13
Write BML#4 Section In Report | 2023-03-10 | 2023-03-13 | bar: 2023-03-10 to 2023-03-13
Iteration 5 - End User Testing 2 | 2023-03-14 | 2023-03-20 | bar: 2023-03-14 to 2023-03-20
Iteration 6 - Eye Tracking App | 2023-03-21 | 2023-03-27 | bar: 2023-03-21 to 2023-03-27
Look into drawbacks and benefits of different eye tracking packages
Create export to offline data functionality
Create backend for caching all data in memory
Iteration 6 - Eye Tracking App | 2023-03-28 | 2023-04-03 | bar: 2023-03-28 to 2023-04-03
Iteration 6 - Eye Tracking App | 2023-04-04 | 2023-04-10 | bar: 2023-04-04 to 2023-04-10
Iteration 7 - Environmental Conditions Test | 2023-04-11 | 2023-04-17 | bar: 2023-04-11 to 2023-04-17
Iteration 8 - | 2023-04-18 | 2023-04-24 | bar: 2023-04-17 to 2023-04-25
Iteration 9 - | 2023-04-25 | 2023-05-01 | bar: 2023-02-15 to 2023-02-20; 2023-04-24 to 2023-05-02
Iteration 10 - | 2023-05-02 | 2023-05-08 | bar: 2023-05-02 to 2023-05-08
Iteration 11 - | 2023-05-09 | 2023-05-15 | bar: 2023-05-08 to 2023-05-16
Iteration 12 - | 2023-05-16 | 2023-05-22 | bar: 2023-05-15 to 2023-05-23
Finishing Report | 2023-05-23 | 2023-05-29 | bar: 2023-05-22 to 2023-05-30
Final Week | 2023-05-30 | 2023-06-05 | bar: 2023-05-29 to 2023-06-05
Hand in final deliverable | 2023-06-05 | 2023-06-05 | bar: 2023-06-05